## Summary
Summary
Areas | Summary of Estimated Requirements (USD)
| Refugee Preparedness | IDP Preparedness | Total
NFI, CBI, Food | 0 | 0 | 0
Health, Education | 0 | 0 | 0
ER, Comms, Inter-Agency | 0 | 0 | 0
Admin, Finance, HR, FSS | 0 | 0 | 0
Protection | 0 | 0 | 0
Supply and Procurement | 0 | 0 | 0
Settlement, Shetler, WASH | 0 | 0 | 0
Data, Registration, IM, IT | 0 | 0 | 0
Programme | 0 | 0 | 0
CCCM | 0 | 0 | 0
Total | 0 | 0 | 0

## NFI-CRI-CBI-Food
NFI/ CRI, CBI and Food
# | Area | Preparedness Actions | Focal Point | Deadline | Estimated Requirements (USD) |  | Comment
[5 empty] | Refugee Preparedness | IDP Preparedness
1 | NFI/ CRI | Agree upon a standard non-food items kit, distribution scale and distribution protocol based on expected profile of population, cultural preferences, climate and environmental considerations, AGD mainstreaming and opportunities to monetize NFI assistance.
2 | NFI/ CRI | Start and maintain capacity building initiatives and dissimination of knowledge with NFI partners/ cluster members on humanitarian standards and cross-cutting issues for an effective NFI response.
3 | NFI/ CRI | Map existing NFI actors and authorities and their available NFI stocks and warehousing locations at a country level.
4 | NFI/ CRI | Assess the need to increase warehouse storage capacity for emergency NFI supplies.
5 | NFI/ CRI | Agree with NFI actors/Shelter and NFI Cluster, on the type of relief items required to be prepositioned including agreed specifications and quantities based on the envisaged contingency planning scenario/ response strategy.
6 | NFI/ CRI | As operational agency or Shelter and NFI Cluster Lead, contribute to the rapid assessment tool and methodology discussions.
7 | NFI/ CRI | Prepare UNHCR's NFI pipeline for emergency supplies.
8 | NFI/ CRI | Assess the capacity to procure locally-sourced NFIs instead of from the global stockpile (if appropriate) as it may be faster and greener to mitigate transport needs.
| NFI/ CRI | Assess the capacity to preposition CRIs (which cannot be procured locally)
9 | NFI/ CRI | Identify the most appropriate NFI strategy in close cooperation with the government and communitities and in consultation with partners/cluster.
10 | CBI | Use CBI as the priority modality of assistance in emergencies, as per the UNHCR 2022-2026 CBI Policy. See https://www.unhcr.org/61fbc91a4
11 | CBI | Design programmatic features of emergency cash assistance in advance: Targeting (to whom?), Transfer value (how much?), Duration (for how long?), and Objective (why - often basic needs)? See https://intranet.unhcr.org/content/dam/unhcr/intranet/protection-operations/cash-based-interventions/documents/english/tools-guidance/CBI%20Repository.pdf
12 | CBI | Establish operating procedures and controls, using template for Standard Operating Procedures for CBI. See https://intranet.unhcr.org/content/dam/unhcr/intranet/protection-operations/cash-based-interventions/documents/english/tools-guidance/CBI%20Repository.pdf
13 | CBI | Ensure Government and local authority engagement and buy-in.
14 | CBI | Secure the availability of a Financial Service Provider: Verify if the existing FSP can cover the emergency response, and if not, start procurement. Ensure the chosen delivery mechanisms can be used for refugees and/or IDPs, as per the Know Your Customer regulations. See https://intranet.unhcr.org/content/dam/unhcr/intranet/protection-operations/cash-based-interventions/documents/english/tools-guidance/CBI%20Repository.pdf
15 | CBI | Ensure registration or enrolment data is available or will be available rapidly: a minima, basic biodata and individual, unique identifier (e.g. proGres ID, national ID credentials) are needed.
16 | CBI | Conduct a light feasibility review (see emergency CBI feasibility review outline). See https://intranet.unhcr.org/content/dam/unhcr/intranet/protection-operations/cash-based-interventions/documents/english/tools-guidance/CBI%20Repository.pdf
17 | CBI | If not yet in use, prepare for the use of UNHCR’s PRIMES tools and CashAssist.
18 | CBI | Engage multi-functional team in UNHCR (Senior Management Leadership and active participation of finance, protection, supply, programme, registration, and technical sectors among others).
19 | CBI | Collaborate with Global Cash Operations/DRS, DFAM, GDS, DESS, and Bureau, to promote contingency planning, solid financial management, traceability, and audit trail.
20 | CBI | Engage in inter-agency cash coordination and Cash Working Group: as per UNHCR’s mandate, coordinate cash response in refugee settings in collaboration with the Government and/or a local partner, and collaborate with cash partners in all settings. Collaboration may include enrolment, piggy backing, assessments, targeting. See Cash Coordination package.
21 | CBI | Review human resources requirements and ensures the operation has adequate CBI and registration personnel available, including for the immediate emergency response.
22 | Food | Identify the gaps in basic food and non-food needs in terms of numbers in need and type of food/non-food assistance required.
23 | Food | Review the potential of using cash as a modality for food and basic needs assistance (in line with new Cash Policy, cash is the preferred modality where feasible).
24 | Food | Only if cash is not possible and in-kind food is required for new arrivals where WFP is not present (yet), identify a nutritionally adequate food basket and commodity sourcing strategy for given time period.
25 | Food | Consider procuring or collaborating with WFP for the procurement of High Energy Biscuits (HEBs) for distribution to new arrivals at border points.
26 | Food | If the anticipated influx is higher than 5,000 refugees, ensure that WFP is fully informed about the population figures, planned protection, settlement and assistance strategy (including CBI) in order for WFP to engage.
27 | Food | Collaborate with WFP to conduct a joint assessment to determine needs and guide a joint food and nutrition response.
|  |  |  | Total | 0 | 0
|  |  |  | Total (report this in first page) | 0

## Health-Education
Health and Education
# | Area | Preparedness Actions | Focal Point | Deadline | Estimated Requirements (USD) |  | Comment
[5 empty] | Refugee Preparedness | IDP Preparedness
1 | Health | The ongoing programme is in line with public health guidelines and protocols (national and international).
2 | Health | Update regularly an analysis of potential health risks for population of concern and related outbreak preparedness and response plans.
3 | Health | Update mapping of Primary Health Facilities and their capacity in areas likely to receive influxes. Identify methods to support these facilities to cater for refugees needs or establish additional facilities where host facilities will not be able to absorb projected population despite upscaling.
4 | Health | Update a mapping of referral facilities and their capacity in areas likely to receive influx. Identify methods to support these facilities to cater to refugees needs, including medicines and equipment, HR and covering referral costs.
5 | Health | Map health stakeholders’ capacities in the areas likely to be affected by the refugee influx to identify potential gaps and opportunities (including public and private facilities, UN, NGOs, Red Cross/Crescent and others). Identify partners to be engaged in upscaling the response as needed.
6 | Health | Establish an interagency inventory of stocks for life-saving medicines, medical supplies and hospital tents. Establish a sourcing strategy for initial response.
7 | Health | Review internal UNHCR staffing capacity at national and local level. Based on existing capacities, including those of partners, propose scale-up solutions for both coordination and implementation.
8 | Health | Consult the ministry of health and contributes to their preparedness plan for refugee influx.
9 | Education | Agree with UNICEF on the priciples on which the education response (e.g. inclusion of displaced learners in the national education system) and seek out an early indication of the nature of UNICEF's operational engagement in this response.
10 | Education | Agree upon leadership/co-leadership responsibilities for education response coordination at national and sub-national levels.
11 | Education | Establish contact with the education coordination mechanism for IDPs (cluster, if activated) and contribute to ensure that UNHCR's protection analysis informs planning and actions. |  |  |  |  | For IDP Situations
12 | Education | Identify government focal points for the emergency response in the Ministry of Education (and higher education) at national and sub-national levels.
13 | Education | Undertake a light-touch review of the education response context, focusing on the policy environment that will inform the strategic direction of the education response.
14 | Education | Complete mapping of partner capacity (UNHCR-funded and non funded partners) to determine which organizations have the capacity to implement/scale-up education activities in affected areas.
15 | Education | Review existing UNHCR Partnership Agreements to identify partners that could be requested to initiate or expand education activities.
16 | Education | Complete initial briefing with education stakeholders (including development actors) on UNHCR's preparedness work for possible influxes.
17 | Education | Determine whether new educational infrastructure will be required in affected areas (newly-built schools; renovation or expansion of existing schools).
18 | Education | Request a briefing on the educational situation in the area/region from which persons are being displaced in order to understand levels of educational disruption prior to displacement in order to inform the development of the response strategy. The briefing should also include information on the structure of the education system and key grades at which examinations are conducted.
19 | Education | Ensure that UNHCR is able to identify teachers and education personnel during registration (where UNHCR is responsible for registration) and capture this information systematically.
20 | Education | Identify national education support programmes (including accelerated education, language learning, and teacher development programmes) that could be extended to displaced learners and hosting communities in coordination with UNICEF, the Ministry of Education, and other partners.
21 | Education | Obtain information on education development programmes implemented in the hosting areas so as to advocate for projects to be potentially expanded to include newly displaced persons.
|  |  |  | Total | 0 | 0
|  |  |  | Total (report this in first page) | 0

## ER-Comms-Inter-Agency
ER-Comms and Inter-Agency
# | Area | Preparedness Actions | Focal Point | Deadline | Estimated Requirements (USD) |  | Comment
[5 empty] | Refugee Preparedness | IDP Preparedness
1 | External Relations | Identify focal point/s within Operation (usually ER and/or PI/Comms) to alert DER (Emergencies and External Engagement - EEE) about any looming emergency, and clear holding statements/key messages/resource mobilization assets drafted with/by DER. (EEE will inform the rest of DER)
2 | External Relations | Ensure contingency plans include comms/resource mobilisation/inter-agency support.
3 | External Relations | Coordinate with Regional Bureau and DER (EEE, GCS, DRRM, PSP, PCS) to timely develop positioning, key messaging, if-asked lines, fundraising/advocacy content gathering capacity and plan, resource mobilization appeals, and other assets and engage with media, public/private donors and other external actors.
4 | External Relations | Ensure sufficient stock of visibility materials (e.g. flags, hats, vests, armbands, tshirts) across field offices and sub-offices, and order additional materials if required.
5 | External Relations | Identify in-kind resourcing needs that can be shared with and sourced from donors as recordable contributions
6 | External Relations | Liaise with DER and be familiar with PI Protocols, UNHCR internal/external reporting mechanisms and templates, UNHCR web page updating procedures during emergencies, Donor Visibility Guidelines, Communications requirements listed in UNHCR IDP Policy Guidance Package, and engage in inter-agency communication fora and public/private donor fora if they exist (e.g. UN Communication/PI WG).
7 | External Relations | Develop/adapt a UNHCR communication/resource mobilization and reporting strategy and tools (external and internal) and train the relevant staff. Identify the spokespeople (and various languages spoken) in the Operation and equip them to engage media and to ensure visibility and promotion of UNHCR preparedness and emergency response. Agree on information exchange between UNHCR and UNHCR-led clusters (where activated).
8 | External Relations | Assess feasibility for high-quality multimedia (photo/video) content gathering missions, including staff capacity and security/access considerations for 1) operation staff; 2) GCS HQ content mission; or 3) local crew, identifying and rostering local crew and fixer in advance where feasible). Situation-dependent, a crew may require a local fixer, translator, photographer, videographer, producer, and writer - some roles may be overlapping.
9 | External Relations | Agree upon and adopt a protocol on media/donor engagement and mission management at country and sub-office level (including sensitization, provision of technical media guidelines and standards for reporting on SGBV, children etc. in humanitarian contexts).
10 | External Relations | Provide key UNHCR staff across operation with guidance on comms/PI and ER/donor relation (including mission management) requirements in situations of emergencies and provide training on the use of essential PI equipment (e.g., smartphone to take photos for visibility products). Seek guidance from DER as needed (including reference to technical media guidelines, and standards for reporting on SGBV, children etc. in humanitarian contexts).
11 | External Relations | Update the operational (and situational, if applicable) factsheet with information on existing programming and short ‘impact’ information e.g. cumulative assistance provided to date that year. Ensure the factsheet is uploaded to Global Focus/Operational Data Portal.
12 | External Relations | Update contact lists for: 1) UN agencies and partners (including relevant development and private sector actors); 2) Embassies and donor focal points at national and regional levels; 3) National and international media.
13 | Inter-Agency | Carry out emergency risk analysis at least once per year together with key partners, and establish inter-agency early warning group to regularly scan the situation and update all partners on risk trends if risks is medium or high.
14 | Inter-Agency | Agree on coordination structure for refugee/IDP emergency with the Government and partners and be ready to activate it in line with the Refugee Coordination Model/UNHCR-OCHA joint letter and Cluster system.
15 | Inter-Agency | Participate in the UNCT/HCT and keep key partners regularly informed on the risk analysis and early warning information pertaining to new or escalating refugee and IDP emergencies (for IDPs only on Protection, Shelter/NFI and CCCM and in collaboration with OCHA).
16 | Inter-Agency | Brief jointly with key partners and in liaison with DER (EEE, PCS, DRRM, PSP) public/private donors, development actors and other stakeholders on increased risk of refugee/IDP emergency, anticipated need to scale up capacity and preparedness level.
17 | Inter-Agency | Support development of an information management and reporting strategy, tools and guidance for UNHCR and inter-agency products in collaboration with IM colleagues.
18 | Inter-Agency | Engage in inter-agency discussions on anticipatory action pilots.
19 | Inter-Agency | Ensure relevant staff are familiar with inter-agency planning/fundraising tools such as the inter-agency UNHCR-led Refugee Response Plan and OCHA-led Flash Appeal/HRP, and UNHCR's Supplementary Budget/Appeal, etc.
|  |  |  | Total | 0 | 0
|  |  |  | Total (report this in first page) | 0

## Admin Finance-HR-FSS
Admin Finance, HR and FSS
# | Area | Preparedness Actions | Focal Point | Deadline | Estimated Requirements (USD) |  | Comment
[5 empty] | Refugee Preparedness | IDP Preparedness
1 | Admin Finance | Complete assessment of the banking system in the country and possibilities of opening bank account, and review the possibilities of fund transfers and availability of cash for manual cash payments/ expenditures and petty cash.
2 | Admin Finance | Segregation of Duties and Delegation of Authority is up to date and UNHCR staff is familiar with financial management procedures and has relevant access to UNHCR systems according to their segregated duties system.
3 | Admin Finance | Identify the vehicle (light, armoured and heavy) needs. Enquire about process and cost related to import clearance, vehicle registration and minimum/ mandatory local third-party liability insurance as per national law. Check the availability for commercial rental vehicles.
4 | Admin Finance | Update authorized bank signatories to operate all bank accounts and electronic payment systems of the operation.
5 | Admin Finance | Ensure that a cash safe is available at all office sites (cash account or petty cash account) for safe keeping of cash and other important documents.
6 | Admin Finance | Determine whether the financial institutions serving UNHCR country operation have the capacity to continue operating in case of emergency and fully serve UNHCR needs. If not, design alternatives.
7 | Admin Finance | Coordinate with Security to arrange for the maintenance and distribution of first aid kits and fire extinguishers on UNHCR vehicles and premises as per SRMM compliant procedures (and PEP kits as appropriate).
8 | Admin Finance | If an expansion, fit-out work, or new UNHCR offices/ premises are needed, a multi-functional team including Administration, Supply, Security, ICT, ensure that all technical aspects and requirements are in place to ensure that premises can be rapidly established and operational.
9 | Admin Finance | Design a vehicle allocation plan to ensure that Security Risk Assessment (SRA) considers vehicles’ availability in areas where the conditions require and that drivers are trained. Vehicles to comply with SRA requirements.
10 | Admin Finance | Maintain an updated database with visa expiration dates for all personnel to monitor visa issuance processes. Research, record, and keep on file the visa regulations for potential emergency deployments and maintain regular contact with relevant authorities.
11 | Admin Finance | Maintain a stock of essential items necessary to the Office in a designated space; check periodically that the items are usable and in good condition. Ensure additional equipment is available in case of increased workforce.
12 | Admin Finance | Identify adequate staff accommodation facilities that can be rapidly activated, when needed (considering emergency deployments).
13 | Admin Finance | UNHCR senior management/admin engage in technical UN discussion (e.g. in Operational Management Team) on favourable regimes in case of emergencies (e.g. UN Model Custom Agreement; expedited visa processing and customs clearance for relief personnel, goods and equipment; facilitation of relief transport; Exemptions from taxes, duties and fees on relief activities) and keep the Representative updated as appropriate.
14 | Admin Finance | Review the need and location for the establishment of new offices and liaison with other agencies to assess the potential for sharing. Consider connectivity, access, and security arrangements.
15 | Admin Finance | Liaise with HQ/DHR & Regional Bureau to review the classification of newly opening/opened Field offices.
16 | Admin Finance | Identify viable options for personnel accommodation in the field (considering surge deployments), including availability of health facilities and adequate sanitation facilities (duty of care).
17 | Admin Finance | Review the need for visibility material and identify the sources of items.
18 | Admin Finance | Research, record and keep on file the regulations for potential emergency deployments-also identify regulations through liaising with other UN organizations (e.g. through dedicated UNCT Working Groups/ UNCT Operational Management Team). Maintain regular contact with relevant government authorities.
19 | Admin Finance | Identify UN examining physicians, lists of local medical facilities and their capacity (also in locations in which additional offices are being considered), and establish Medical Evacuation Procedures, including in coordination with other UN Agencies (e.g. through UNCT Working Groups/ UNCT Operational Management Team).
20 | Admin Finance | Maintain an up to date administrative briefing kit for new personnel arrivals describing administrative arrangements (working hours, R&R, transport arrangements); key UNHCR documents (CoC, PSEA); information on living conditions, security, local customs; list of health facilities (medical professionals, UN doctors, UN and other clinics and hospitals); key internal- external emergency contacts and other useful facts/ documents.
21 | Admin Finance | Support the senior management in liaising with authorities responsible for visa issuance and maintain contacts to speed up processes during possible surge of staff.
22 | HR | Identify UN Examining Physician and the Establish Medical Evacuation Procedures.
23 | HR | Identify local networks for advertising national vacancies through website, Newspapers, other UN and NGOs.
24 | HR | Proactively search candidates for potential deployment through Workday.
25 | HR | Identify comprehensive staffing needs (including identification of critical roles, and which functions need to be deployed immediately) for the emergency response and familiarize with the staffing structure and procedures to initiate deployments and short-term assignments in emergencies.
26 | HR | Remind personnel to have up to date ID cards, personal documentation, and keep copies in off-site locations.
27 | HR | Disseminate inventory lists and remind international staff to keep them updated for insurance purposes.
28 | HR | Ensure, in cooperation with Security, that all personnel have their mandatory UNDSS security courses up to date.
29 | HR | Establish an in-country roster of staff from UNHCR country operation listing potential deployment capacity, including a stand-by emergency team (in major operations).
30 | HR | Identify additional staffing needs, and plan to request deployments. Start drafting Terms of Reference (ToRs) for additional staff, customised as necessary, in coordination with the respective sections of the country operation.
31 | HR | Consider staff well-being needs in potential emergency situations and provide lists of UNHCR staff counsellor contact details. HR is familiar with the administrative part of onboarding and induction for emergencies.
32 | FSS | Staff safety and security procedures are up-to-date, functioning and drilled - Security Briefings, Security Incident Reporting, Warden System, SOPs, Security Plan, Critical Incident Management Plans, Contingency Plans including Medical Contingencies, Emergency contacts available to all personnel. Staff awareness in relation to personal security responsibilities in respect of all of the above should be emphasised and facilitated. https://intranet.unhcr.org/content/dam/unhcr/intranet/policy-guidance/policies/2020/unhcr-hcp-2020-03/Annex_A_Security_Management_Responsibilities_v3.pdf https://unhcr365-my.sharepoint.com/:x:/g/personal/funckc_unhcr_org/EfAhZUkemMFFr06PKEi6kLMBHU4Ti4Y2lAp7fGSzkVmW9Q?e=rHP1aL&CID=4D125283-DA9B-4BF8-8D47-421E5532FA82
33 | FSS | Facilitate in ensuring compliance with mandatory security training (BSAFE, SSAFE); and all additional relevant and needs-based security training for all staff, e.g., SMLP for senior managers with security responsibilities and accountabilities. BSAFE may be found at: https://training.dss.un.org/
34 | FSS | In coordination with Medical Service, maintain (HR and UNSMS/UNDSS) an up-to-date Medical Evacuation Plan that is ready to be operationalised.
35 | FSS | Consider and integrate security requirements into plans.
36 | FSS | Participate in the Programme Criticality Exercise in high-risk duty stations. Update the Business Continuity Plan accordingly. UNHCR Guide to Programme Criticality.
37 | FSS: Partnership/ UN Security Management System (UNSMS) | Ensure full participation in UN Security Management System at Country Level (SMT); and area level (A/SMT). Keep senior management informed on security recommendations proposed from the A/SMT Area Level. Build and sustain partnerships under the Saving Lives Together Framework (SLT), and with UNDSS from the security viewpoint.
38 | FSS | In coordination with Administration, arrange for the maintenance and distribution of First Aid Kits and Fire Extinguishers in UNHCR vehicles and premises. Coordinate with Medical Services, UNDSS, UNFPA as applicable to the AOR (Area of Responsibility) to ensure all UNHCR Offices have up-to-date PEP Kits, with staff awareness of custodians and administrators in their AORs. https://hr.un.org/page/hiv-pep-kit-management.
39 | FSS: Capacity Development | Ensure compliance with Security Risk Management Measures (SRMMs) in each operational area, advising and informing all UNHCR personnel accordingly on same.
40 | FSS: Capacity Development | Provide a security briefing for new personnel. Coordinate with Admin to ensure that security content in the briefing/orientation document is up-to-date.
41 | FSS: Capacity Development Communication System | Develop and test internal security communication systems (SMS list, radio, etc.) to exchange crisis-specific information.
42 | FSS: Capacity Development | Review and update all security documents in line with UNSMS requirements and changes in the operational threat environment. Maintain relocation /evacuation plans within the Security Plan ensuring implementation modalities are realistic and feasible. Ensure that personnel is aware of lock-down protocols and measures.
43 | FSS: Capacity Development | Coordinate with Admin to ensure implementation of, and adherence to, Residential Security Measures (RSM) applicable for the AOR. Provide technical support and guidance on physical security requirements for UNHCR Offices, warehouses /rub halls, Reception Centres, camp activities and Settlements
44 | FSS: Capacity Development | Assist management from the security technical standpoint in assessing the need for additional office and accommodation facilities that can be rapidly activated, when needed.
45 | FSS: Capacity Development | Cooperate with Administration and Supply in the identification of additional vehicle needs 4x4 light vehicles, and armoured vehicles (AVs) as required. For AVs, also consult with the FSS Structural Engineer - BAKI@unhcr.org
|  |  |  | Total | 0 | 0
|  |  |  | Total (report this in first page) | 0

## Protection
Protection
# | Area | Preparedness Actions | Focal Point | Deadline | Estimated Requirements (USD) |  | Comment
[5 empty] | Refugee Preparedness | IDP Preparedness
1 | Protection: Context/ Risk Analysis | Provide information gathering and analysis on the overall protection situation, emerging risks/ risk areas/ groups at risk, and other trends at country level. This information supports the management of UNHCR Country Operation to define/ contribute to scenario building, early warning, and preparedness/ contingency planning through regular protection monitoring, interactions with affected (and displaced if already present) communities, various civil society organizations |  |  |  |  | Refugee situations: - UNHCR scenario and contingency planning for inter-agency refugee response and for UNHCR agency-specific response IDP situations: - UNHCR (as protection agency and Cluster Lead) participation to interagency WG on risk monitoring/ early warning - UNHCR contribution to inter-agency scenario/ contingency planning at national or sub-national level
2 | Protection: Context/ Risk Analysis | Maintain contacts with UNHCR in neighboring countries and relevant Regional Bureaux, to obtain/ provide early warning on population movements and profile. |  |  |  |  | Refugee situation in particular
3 | Protection: Context/ Risk Analysis | Establish and maintain regular contact with key border management authorities (border authorities, immigration, national security, customs, etc.), and civil society actors present in border areas. |  |  |  |  | Refugee situations
4 | Protection: Context/ Risk Analysis | Compile and update information on the country legal, policy and institutional framework relevant to a potential emergency protection response--including conditions and procedures for access to territory and to asylum, border management, policies/laws (including policies on internal displacement), emergency and national protection systems. Create a depository available for UNHCR. |  |  |  |  | Refugee situations - UNHCR as refugee lead agency IDP situations - UNHCR, including as Cluster lead (and AoRs), if activated
5 | Protection: Context/ Mapping | UNHCR or the Protection Working Group or Protection Cluster (if activated) update a mapping of key protection partners and authorities (presence, service offered, AGD inclusiveness, and response capacity) as a basis for developing/ updating referral pathways for individuals with specific protection needs (GBV, child protection, disability, LGBTIQ+, others). |  |  |  |  | Refugee situations and IDP situations (UNHCR as sector/cluster lead and internally)
6 | Protection: Contingency Planning/ UNHCR | As part of the Multi-Functional Team, UNHCR protection staff in the Country Operation, including those with specialized technical expertise (CP, GBV, Protection Coordinator if Clusters activated), actively participate in the discussion and drafting of UNHCR’s contingency planning. Protection staff contribute to review and define the Country Operation’s contingency planning by including protection interventions, supporting the inclusion of protection considerations (AGD, GBV risk mitigation, CP) in the planned response, and highlighting related human and financial resources to be mobilized. |  |  |  |  | Refugee situations and IDP situations (UNHCR internally)
7 | Protection: Contingency Planning/ UNHCR | Undertake a review of UNHCR Country Operation internal organizational capacity in protection and identify tentative staffing needs for protection delivery in the emergency, including Child Protection and GBV staffing. (For protection sector/ cluster coordination see also activity 25) |  |  |  |  | Refugee situations and IDP situations (UNHCR internally)
8 | Protection: Contingency Planning/ Protection Sector-Protection Cluster | With the partners of an existing national Protection Working Group (or Protection Cluster Working Group where the IASC Cluster System is already activated) start to outline a Sector / Cluster protection response strategy and related activities, including GBV and CP, based on established practices and standards. This planning is integrated in any UNHCR-led inter-agency preparedness/contingency planning (refugee situations) or inter-cluster contingency planning (IASC ERP approach). |  |  |  |  | Refugee situations and IDP situations (UNHCR as sector/cluster lead)
9 | Protection: Contingency Planning/ Protection Sector-Protection Cluster | In countries already hosting refugees, where GBV and CP sub-sector working groups may already exist, outline an initial GBV or CP response strategy and related interventions with members of the respective sub-sector working groups. |  |  |  |  | Refugee situations and IDP situations (UNHCR as sector/cluster lead)
10 | Protection: Protection Systems/ Standards and Procedures | Engage national authorities in discussion on international refugee protection, on the status of possible new refugee influxes, on non-refoulement, on the civilian character of asylum, advocating for upholding legal and procedural standards in international protection. |  |  |  |  | Refugee situations
11 | Protection: Protection Systems/ Standards and Procedures | Bilaterally or through interagency initiatives (in IDP settings) engage in a dialogue with relevant authorities and advocates for protection considerations, including protection of civilians, and for Minimum Standards (e.g. GBV, CP) to be included in the authorities’ emergency response. |  |  |  |  | Refugee situations and IDP situations
12 | Protection: Response Capacity/ Border Monitoring | Design and, where possible, establish border monitoring system, making use of UNHCR’s protection monitoring toolkit and UNHCR starts training of engaged partners |  |  |  |  | Refugee situations
13 | Protection: Response Capacity/ Emergency Protection Monitoring | Work to establish or reinforce emergency protection monitoring capacity, making use of UNHCR’s protection monitoring toolkit (i.e. tools for border monitoring, emergency IDPs or refugee situations) and start training funded partners and other protection partners (if relevant) |  |  |  |  | Refugees and IDP situations
14 | Protection: Response Capacity/ Multi-Sector Needs Assessments | Contributes to preparatory discussions regarding inter-agency common assessments methodologies and tools; advocate to include right-sized protection-related and protection-specific information; recommend methodologies that include participatory and AGD-sensitive approaches; recommend general principles and specific standards of ethical data collection and standards of safe, ethical, and effective management of data for operational response. |  |  |  |  | Refugee situations IDP situations (e.g. Assessment WG)
15 | Protection: Resonse Capacity/ Emergency Registration | Agree on adequate emergency registration procedures with the Government and put in place data sharing procedures |  |  |  |  | Refugee situations
16 | Protection: Resonse Capacity/ Emergency Registration | Develop sourcing strategy for personnel, materials, structures for emergency registration, and ensure the emergency registration stocks for the first days of response are available in-country. |  |  |  |  | Refugee situations
17 | Protection: Response Capacity/ Capacity Development | Engage, as needed and already feasible, in capacity development initiatives for national and local authorities and partners on protection themes/ issues (e.g. AGD, CP, GBV), based on the scenario identified and the type of protection response foreseen. |  |  |  |  | Refugee and IDP situations
18 | Protection: Response Capacity/ Procedures | Undertake, where appropriate and already possible, the development of SOPs in line with UNHCR and IASC standards for certain interventions (e.g., GBV, Child protection/BIP, disability, LGBTIQ+ etc.) |  |  |  |  | Refugee and IDP situations
19 | Protection: Response Capacity/ AAP | Identify information needs, preferred communication modalities and channels, and related challenges. Develop a plan for a two-way communication with communities, including key outreach messaging to be disseminated through protection and other partners. (e.g., on family separation, child safety and well-being, MHPSS, GBV risks, various types of available protection services, Mine Risk Education) |  |  |  |  | Refugee and IDP situations (including at interagency level and within the Protection Sector/Cluster)
20 | Protection: Response Capacity/ AAP | Develop/update/reinforce community feedback and response mechanisms, including on sensitive complaints, and related operating procedures |  |  |  |  | Refugee and IDP situations
21 | Protection: Response Capacity/ AAP | Identify and sensitize community-based protection networks (monitoring, identification, ethical referrals) , including from organizations led by women, persons with disabilities, LGBTIQ+, youth, forcibly displaced etc., who can support outreach interventions at the onset of the emergency |  |  |  |  | Refugee and IDP situations
22 | Protection: Protection and CBI | UNHCR protection staff participate in UNHCR internal (and/or inter-agency Cash Working Groups) dialogue and preparedness / scoping exercises in relation to possible CBI initiatives, contributing to identify protection risks and benefits and integrating protection in any foreseen targeting approach. |  |  |  |  | Refugee and IDP situations
23 | Protection: Protection Coordination | Authorities, UNHCR protection partners, and other protection actors receive briefings on the Refugee Coordination Model or on the IASC Cluster system, as appropriate, particularly on the role and responsibilities of UNHCR in support to the Government and /or as Protection Cluster lead agency. |  |  |  |  | Refugee situations - Refugee Coordination Model IDP Situations - IASC Cluster Approach (if not activated)
24 | Protection: Protection Coordination/ Protection in RCM | Reach agreement on UNHCR/Government-led Refugee Protection Working Group (and related sub-sectors as required) at national and at sub-national level, as appropriate. |  |  |  |  | Refugee situations
25 | Protection: Protection Coordination/ Cluster Activation | Discuss possible cluster activation, coordination configuration (national and sub-national level coordination), and co-leadership/ co-facilitation arrangements with key protection agencies, including national/local actors |  |  |  |  | IDP situations (where Cluster not yet activated)
26 | Protection: Protection Coordination/ Staffing considerations | UNHCR Representative and senior protection management, in coordination with Regional Bureaux, discuss options for increasing the Country Operation’s staffing capacity in protection sector/ cluster coordination (including IM) and informs DESS/ DIP accordingly |  |  |  |  | Refugee situations and IDP situations (where Cluster not yet activated)
|  |  |  | Total | 0 | 0
|  |  |  | Total (report this in first page) | 0

## Supply and Procurement
Supply and Procurement
# | Area | Preparedness Actions | Focal Point | Deadline | Estimated Requirements (USD) |  | Comment
[5 empty] | Refugee Preparedness | IDP Preparedness
1 | Supply | Research, record and keep on file customs clearance regulations and procedures and establish contacts with the relevant Government focal points.
2 | Supply | Establish a special import regime (i.e. waivers) for relief goods during the emergency as necessary.
3 | Supply | Conduct a market survey of national/local suppliers for relief items and shelter/wash materials, Financial Service Providers, waste management services, heavy machinery and transport services (if applicable). Update and maintain a vendor list/database, including contact details. Include sustainability aspects (environmental, social and economic) in market surveys
4 | Supply | Ensure that the supply/ technical team/ requesting units are familiar with emergency supply and procurement procedures.
5 | Supply | Establish local supply frame agreements for items that may be needed in the emergency and delivery mechanisms. Ensure those suppliers have sustainable practice in place. Maintain an updated list of frame agreements.
6 | Supply | Establish a sourcing strategy and comprehensive procurement plan for goods and services, covering three months of assistance, based on the contingency plan. Prioritize the use of greener specifications
7 | Supply | Locate the minimum calculated level of relief item stocks in country, and analyze regional stock and/or neighbouring country operation stock based on the contingency plan considering the accountability of UNHCR as “Provider of last resort” (where clusters are activated).
8 | Supply | Establish an inter-agency logistics coordination group, led by UNHCR supply with key partners to review capacities and identify gaps.
9 | Supply | Liaise with other UN Agencies (UNCT/ OMT, other UN joint platforms for common procurement/ Common Procurement Teams, joint mailing lists) to obtain and contribute to relevant information sharing on national legislation, procurement agreements in place, logistics/transport (including cooperation with border authorities, aviation authorities, etc.), warehousing, sustainable goods and services (specifications, contracts), waste management services, etc.
10 | Supply | Collect and file a depository of import/customs clearance legislation, regulations and procedures, including common UN Custom Agreements (if in place).
11 | Supply | Establish contacts with relevant Government focal points for import and custom clearance for goods and transports, and develop SOPs or adopt and follow UN Common procedures/ SOPs.
12 | Supply | Ensure that the supply team is familiar with emergency procurement and supply procedures and conditions (including the role of the Logistic Cluster) and put in place necessary committees.
13 | Supply | Arrange and update DOAP in line with appropriate segregation of duties.
14 | Supply | Periodically brief and train partners on UNHCR procurement procedures, including pre-qualification for procurement which are provided by UNHCR Supply – in cooperation with UNHCR Program and project control - when required.
15 | Supply | Conduct a market survey of national/local suppliers for relief items and other material. Update a vendor list/database, including existing UNHCR Local Frame Agreements or available Frame Agreement with other UN Agencies in country (including contact details). Exchange information with the UN Common Procurement WG (if existing). Ensure sustainability aspects are considered when sourcing.
16 | Supply | Cooperate within the MFT to define sourcing plans and discuss options for local Procurement (Local Frame Agreements) and/ or other procurement/ supply options (e.g. Global Stockpiles, Global Frame Agreements).
17 | Supply | Participate in UNHCR internal discussions on CBI feasibility assessments.
18 | Supply | Ensure that UNHCR staff and all other personnel managing warehouses (e.g. focal points from partners or commercial entities if applicable) are in place and trained in warehousing procedures/ management; and establish a warehouse storage; update the MSRP Inventory Module; and conduct periodical physical verifications. Ensure energy efficiency measures, minimize waste and reduce single-use plastic.
19 | Supply | Through IM support, maintain an updated internal mapping of UNHCR warehouses in the country, stocks etc. at country and at regional level (in cooperation with RB).
20 | Supply | Maintain an updated assessment of modes of local transportation available (air, road, rive/sea etc.), road infrastructure and road transport capacity as well as availability of airports, adequacy of airport infrastructures etc. Consider reduced travel distance and transport modes with low emissions.
21 | Supply | Ensure attendance of UNHCR focal points in the Logistic Cluster meetings and other relevant Clusters (Shelter/NFI in particular) to ensure engagement and collaboration on all areas of logistics, including transport (also air transportation), warehousing capacity, asset management, clearance formalities etc.
22 | Supply | Maintain regular contacts with UNHCR-led Shelter Cluster to exchange information on mapping of stocks and warehousing from other humanitarian partners.
23 | Supply | Participate in and support (including by chairing) UN Common Procurement Working Groups and/or Logistic Cluster taking preparedness actions.
24 | Supply | Establish local supply frame agreements for transportation, fuel, supply and other frequently purchased goods and services, to be active for the foreseen emergency, also in coordination with the UN Common Procurement WG. Maintain an updated list and share it with existing UN Common procurement WG. Select vehicles with low emissions
25 | Supply | Where CBI initiatives is the agreed response modality, take steps to procure financial service providers, ensuring collaborative approach to procurements (through joint procurement with other agencies or by including collaboration clause to its own procurement). If UNHCR and/or partners already have a contract with a Financial Service Provider, the contract should be used. Select suppliers with sustainable practices in place.
26 | Supply | Review the adequacy of UNHCR supply and logistic structure and determine the need for any additional transportation/ logistic/warehousing capacity or the opportunity to share warehouse space and logistic assets with other humanitarian actors in line with 1) the foreseen volume of goods/ items to be procured and received, 2) UNHCR warehousing capacity and 3) discussions with other UN Agencies on respective logistic capacities (through the Logistic Cluster, if activated).
27 | Supply | Identify additional Vehicle needs: 4x4 light vehicles, Armoured vehicles (when needed) and minibus, considering custom clearance process, plate registration, insurance and the availability for rental vehicles (also in coordination with other UN Agencies/ OMT etc. Select vehicles with low emissions
28 | Supply | Provide, in cooperation with the Regional Bureau and DESS, UNHCR Country Operation with human resources and capacity, for UNHCR in-country Supply and technical functions, including in information management.
29 | Supply | Coordinate internally with Shelter, Field/ Operations, Program and share information with UNHCR-led Shelter Cluster Coordinator (if activated) on existing in-country stocks.
|  |  |  | Total | 0 | 0
|  |  |  | Total (report this in first page) | 0

## Data-Registration-IM-IT
Data, Registration, IM and IT
# | Area | Preparedness Actions | Focal Point | Deadline | Estimated Requirements (USD) |  | Comment
[5 empty] | Refugee Preparedness | IDP Preparedness
1 | Registration | Prepare for the delivery of efficient protection and assistance through registration of each household and individual. This is critical e.g. for cash assistance, to know who is being served, and to avoid fraud and duplication. |  |  |  |  | It is also important for referrals, case management, issuing documentation and managing assistance, including for cash.
2 | Registration | Partner with Governments, other UN Agencies, NGO's and private companies during set up or scale up of registration to cover for registration staff, registration centers, ICT equipment, IT infrastructure, office equipment, transport, security, logistics, information campaigns, etc.
3 | Registration | Develop proper registration strategies, including budgets and HR, to avoid delays in registration which directly impact on the roll out of assistance programs.
4 | Registration | Consult the UNHCR Registration Checklist for Emergencies for a comprehensive list of tasks and considerations. Some of the time-consuming tasks, which can be done in advance include agreeing on the role of the various partners, in particular the Government. Prepare MoU’s and data sharing agreements.
5 | IM: Data Preparedness | Ensure that pre-crisis data is available, along with the list of existing data capacity (i.e., staff and materials), data sources, data activities and their owners, and CODs for the country of asylum and country of origin (or areas of origin and displacement in the case of internal displacement).
6 | IM: Data Preparedness | Identify, compile and make ready emergency IM guidance, tools and products, such as needs assessments, Flow Monitoring (and other types of population data management), Protection Monitoring in Emergencies, and CORE.
7 | IM: Data Preparedness | CORE is enhanced IM for emergencies. It includes the creation and release of external products. Operations should determine whether additional staff capacity is needed to create these products and manage the underlying data systems providing information on population movements, needs, and response.
8 | IM: Coordination | Strengthen the ability of response actors to develop and implement a coordinated IM response in an emergency. This could involve conducting capacity building for local and international actors, assessing data-related resource needs for different emergency scenarios, establishing contacts with relevant government authorities, and establishing or strengthening an IMWG. The IMWG can make early preparations related to data and information sharing, establishing common typologies, and agreeing on common tools and services (e.g. ODP, 3/4/5Ws, joint assessments, etc.).
10 | Population data | Produce forward looking population estimates and assess the likely magnitude and extent of the displacement.
11 | IT | Trigger an assessment of the IT needs and gaps in the country using the IT Assessment Report Template for Preparedness.
12 | IT | Establlish and maintain contact with the IT focal points of UN agencies and other partners in country to initiate an inter-agency IT Working Group (ITWG). Actively engage with ITWG to ensure that the Group serves as a forum for all matters relating to IT and communications.
|  |  |  | Total | 0 | 0
|  |  |  | Total (report this in first page) | 0

## Settlement-Shelter-WASH
Settlement, Shelter, and WASH
# | Area | Preparedness Actions | Focal Point | Deadline | Estimated Requirements (USD) |  | Comment
[5 empty] | Refugee Preparedness | IDP Preparedness
1 | Shelter: Opperational | Plan housing assistance based on expected influx/scenarios at national level and at critical locations, in close consultation with relevant government entities and in line with UNHCR policies.
2 | Shelter: Opperational | Pursue alternatives to camps to the maximum possible extent.
3 | Shelter: Opperational | Consider CBI as a first option to cover accomodation needs.
4 | Shelter: Opperational | Plan accomodation and housing assistance in a way that mainstreams protection aspects (including age, gender, diversity, and GBV risk mitigation), provides safety, privacy, dignity, tenure security, encourages participation and empowers both forcibly displaced and local communities.
5 | Shelter: Opperational | Identify accomodation and housing options based on local context, rules and regulations, cultural preferences of forcibly displaced, climate considerations, (in)stability, capacity to scale up a response in case of a sudden-onset influx, etc.
6 | Shelter: Opperational | Factor into the plan ties with local communities which may result in favorable hosting arrangements.
7 | Shelter: Opperational | Consult closely with CBI staff, and ensure that HH level monthly cost covering rent and other accomodation needs are defined and considered under MPCA. Capture requirements for housing assistance in market assessments.
8 | Shelter: Opperational | Agree upon a standard emergency shelter kit, distribution scale and distribution protocol, when relevant.
9 | Shelter: Opperational | Identify and map existing and potential critical locations to host forcibly displaced or to facilitate further movements (border crossing points, transit and reception centres, and settlement locations).
10 | Shelter: Opperational | Map current population, services, infrastructures, reception capacity and possibility for expansion.
11 | Shelter: Opperational | Carry out multi-sectorial assessments, also with the involvement of local authorities.
12 | Shelter: Opperational | Factor into the plan technical challenges or risks (e.g. locations at risk of floods, landslides, cyclones, water scarcity, earthquakes, structural instability, fire hazard, etc.) and, if needed, consider alternative locations in advocacy efforts with government authorities.
13 | Shelter: Programmatic | When relevant, contract and have on stand-by suppliers for (rental of) containers, heavy earth moving equiptment (for clearing land and access roads) and other essential contruction equiptment.
14 | Shelter: Programmatic | Review internal UNHCR staffing capacity at national and local level. Propose scale-up solutions (emergency roster, stand-by partner arrangement, etc.) based on existing capacities, including those of partners, for both implementation and coordination. |  |  |  |  | Refugee response; for IDP's please refer to the Global Shelter Cluster
15 | Shelter: Programmatic | Map UNHCR's available and potential pipelines for emergency shelter and related warehouse needs.
16 | Shelter: Coordination | Map at a country level shelter actors presence with current and projected response capacities (staffing, pipelines, warehousing) at national and subnationa/local levels.
17 | Shelter: Coordination | Closely involve relevant government focal points at the national and sub-national levels in preparedness activities.
18 | Shelter: Coordination | Make donors aware of projected challenges/gaps/needs in housing and settlement assistance under broader, management-led coodination umbrella.
19 | Shelter: Coordination | Review IM capacity and needs.
20 | Shelter: Coordination | Plan/start/continue capacity building initiatives and dissemination of knowledge with relevant partners and government entities on humanitarian standards and cross-cutting issues for an effective housing response.
21 | WASH: Opperational | Plan WASH assistance taking into consideration, among other factors: local context, rules and regulations, cultural preferences of forcibly displaced, climate considerations and environmental risks, (in)stability, capacity to scale up a response in case of a sudden-onset influx.
22 | WASH: Opperational | Plan WASH assistance in a way that can mainstream protection aspects (including age, gender, diversity and GBV risk mitigation), provide safety, privacy, dignity, encourage participation and empower both forcibly displaced and local communities.
23 | WASH: Opperational | Quantify required WASH assistance based on expected influx/scenarios at national level and at critical locations: overall water needs, including information on critical areas subject to/at risk of water scarcity; sanitation facilities required, including any technical challenge (types of soil, groundwater depth, etc.); hygiene items needed (depending on family size and composition, cultural preferences, availability of items, length of stay, etc.), including via CBI as preferred modality.
24 | WASH: Opperational | Analyze community practices around water, sanitation and hygiene. Factor in relevant assistance tailored to preferences and needs of the affected population, including for those at high vulnerability (children, elderly, PLW, people with reduced mobility, and other PwSN) into WASH preparedness.
25 | WASH: Opperational | Undertake WASH field visits (as part of inter-sectorial work) at border crossing points, transit centres, accommodation/ reception/ settlement locations, hosting arrangements, etc.
26 | WASH: Opperational | Map potential water sources for water supply.
27 | WASH: Opperational | Where cash is not feasible/relevant (e.g. when formal settlements are envisaged), identify in collaboration with Supply and Programme the sourcing strategy for WASH materials, contractors, and partners. This shall cover: water provision-via connection to and repairs of existing water systems, drilling of new boreholes, etc.; rapid provision/contruction of WASH facilities (toilets, showers, hand washing points): this could be via istillation of prefabricated solutions (e.g. equipped containers/prefabs), newly constructed facilities or upgrading of existing ones (particularly for existing transit and reception centres, and formal settlements); wastewater management via connection to and repair of existing wastewater systems and prompt and sufficient desludging if required; provision of hygiene items. Above shall take into consideration existing and projected capacity of existing partners. | [5 empty] | Link available?
28 | WASH: Programmatic | Consider the use of cash in line with the UNHCR 2022-2026 CBI Policy: in close consultation with CBI staff, define and consider HH level monthly cost to cover WASH needs under MPCA. Capture requirements for WASH assistance in market assessments.
29 | WASH: Programmatic | Review internal UNHCR staffing capacity at national and local level. Based on existing capacities, including those of partners, scale-up solutions are proposed (emergency roster, stand-by partner arrangement, etc.), for both coordination and implementation.
30 | WASH: Programmatic | Map at a country level the presence of a) WASH actors with current and projected response capacities (staffing, pipelines, warehousing) at national and sub-national/local level. b) Government focal points relevant for WASH at national and sub-national levels involved in preparedness. Discuss sector coordination arrangements at national and sub-national/local levels, based on capacities and presence.
31 | WASH: Programmatic | Make donors aware of projected challenges/gaps/needs in WASH under broader, management-led coordination umbrella.
32 | WASH: Programmatic | Prepare standard WASH assessments tailored to the specific context. Review IM capacity and needs for the WASH sector.
33 | WASH: Programmatic | Identify capacity-building needs and provide support depending on the context and identified knowledge gaps.
|  |  |  | Total | 0 | 0
|  |  |  | Total (report this in first page) | 0

## Programme
Programme
# | Area | Preparedness Actions | Focal Point | Deadline | Estimated Requirements (USD) |  | Comment
[5 empty] | Refugee Preparedness | IDP Preparedness
1 | Programme | Ensure relevant colleagues (Protection, Operations) are familiar with programme management in emergencies, including management of partnerships.
2 | Programme | Contribute to the emergency risk analysis within the Annual Risk Review.
3 | Programme | For the contingency plan, consolidate the separate budget requirements; for UNHCR preparadness actions and for UNHCR emergency response activities (OP budget).
4 | Programme | Support sector specialists and partners to prepare an interagency rapid needs assessment plan, inclusive of the methodology and activation procedures, that would capture essential data for the emergency response.
5 | Programme | Support sector specialists and partners to identify priority projects/activities that target host communities in order to enhance absorption capacity.
6 | Programme | Contribute to assessing and recommending effective establishment, implementation, coordination and management of UN joint initiatives and common services.
7 | Programme | Cooperate with Supply in defining the sourcing strategies and procurement plans for the emergency, based on the scenario-based contingency plan.
8 | Programme | Plan to allocate budget for future replenishment of core relief items, if applicable.
9 | Programme | Review existing project partnership agreements, alongside the strategic planning’s stakeholder mapping, at the time of contingency planning, in order to identify potential gaps in expertise/services, the scope of required results and geographical place of delivery during the emergency.
10 | Programme | Lead discussions with partners on the necessary amendments required to their project partnership agreements in response to the emergency so that any concerns surrounding the potential changes in their scope of work and subsequent impact on the partners’ capacity to deliver is addressed.
11 | Programme | Expedite a call for expression of interest (CfEoI) for a pool of potential partners to be engaged, when needed, during the foreseeable length of the emergency period.
12 | Programme | Lead briefings with new potential partners on UNHCR partnership procedures in order to familiarise themselves with the avenue for cooperation with UNHCR.
13 | Programme | Ensure IPMC-recommended partners for the pool have undertaken applicable assessment processes, including PSEA and procurement capacity, where applicable to the type of activities to be implemented during the emergency.
14 | Programme | After the CfEoI, establish the pool of potential partners that have been recommended by the IPMC.
15 | Programme | Support new partners from the pool to register on the UN Partner Portal as soon as possible (if applicable).
16 | Programme | Establish new partnership agreements based on the stakeholders’ mapping and based on the recommendation of the IPMC, in response to the emergency.
17 | Programme | Lead briefings with private sector actors on UNHCR partnership procedures in order to familiarize them with the avenue for cooperation with UNHCR.
18 | Programme | Manage budgets flexibly to ensure an immediate operational response to the emergency.
19 | Programme | Update (or develop where not already in existence) the annual monitoring and evaluation activity workplan to determine the key monitoring and activities required for partnerships during the emergency. |  |  |  |  | NB: There are no reduced implementation and results monitoring requirements during an emergency, and the frequency of monitoring activities may increase.
|  |  |  | Total | 0 | 0
|  |  |  | Total (report this in first page) | 0

## CCCM
CCCM
# | Area | Preparedness Actions | Focal Point | Deadline | Estimated Requirements (USD) |  | Comment
[5 empty] | Refugee Preparedness | IDP Preparedness
1 | CCCM | Analyze information on displacement management, including at sub-national level with UNHCR-led CCCM Cluster/working groups.
2 | CCCM | Familiarize selected partners and UNHCR-led CCCM Cluster/Working group with camp management, approaches and tools in various contexts and adapt existing capacity building materials to the country context. Support dissemination and completion of the CCCM e-learning.
3 | CCCM | Undertake a mapping of existing humanitarian actors including government entities and faith-based organzations at country and sub-national level with expertise in displacement management, and their current /potential capacity in camp management/ camp coordination with UNHCR-led CCCM Cluster/Working group.
4 | CCCM | (If formal or informal camps/sites and collective centre are already existing) Establish and maintain a list and service profile of all existing camp/sites and other communal settings with concentration of displaced population and facilitate regular updating of the list through inter-agency processes.
5 | CCCM | Based on the initial general analysis, engage in further analysis on the most likely emergency scenario unfolding with more in-depth assessment.
6 | CCCM | Consider challenges and opportunities represented by camps/ sites as emergency response modality. UNHCR’s analysis informs the inter-sector/cluster and the UNCT/ HCT discussion and ultimately the inter-agency contingency planning (IASC ERP approach).
7 | CCCM | Regularly update senior management based on analysis and discussion at inter-agency/ inter-cluster level, to ensure inclusion in dialogue with national/local authorities on the CCCM strategy and contingency measures in the foreseen displacement-affected areas. This informs the inter-agency contingency planning (IASC ERP Approach).
8 | CCCM | Prepare a response strategy focused on intervention across a multitude of highly fragile collective settings in spontaneous structures within informal rural or urban contexts as CCCM operational agency or Cluster Lead (when activated). |  |  |  |  | In the context of displaced population settling in camp-like situations
9 | CCCM | As operational agency (Field/ CCCM and Site Planning) or Cluster Lead (if activated), coordinate actions to identify/ assess/ agree on potential camp locations, coordinate the security arrangements and ascertains the role of the national authorities, coordinate the identification of actors to exercise camp management functions, facilitate the planning and the implementation of multi-sectoral rapid needs assessments, coordinate with humanitarian actors to ensure capacity for adequate presence and service provision. |  |  |  |  | In the context of the establishment of IDP Camps as the most appropriate temporary accommodation for IDPs in the planned emergency response
10 | CCCM | As operational agency or CCCM and Protection Clusters Lead (if activated) start to sensitize authorities and advocate for measures to preserve the civilian and humanitarian character of camps/ sites (including measures in relation to civilian administration, security screening processes, freedom of movement for camp population, separation of armed elements). |  |  |  |  | In the context of planned camps/ sites as planned emergency response
11 | CCCM | Adapt to the envisaged emergency context the existing CCCM tools designed to assess needs, to map and facilitate coordination of service provision, to detect gaps in service provision, to share information on available services and to track population movements at camp/ site level (tools available from the Global CCCM Cluster or already developed for other situations in country).
12 | CCCM | As operational agency or CCCM Cluster lead (if activated) maintain a mapping of the presence of authorities and of humanitarian actors suitable for management and site-level coordination in areas likely affected by the IDP emergency and on how their presence and capacity may be affected. |  |  |  |  | In the context of planned camps/sites as planned emergency response
13 | CCCM | As operational agency or CCCM Cluster Lead (if activated) reinforce capacity development initiatives for authorities at various levels to take on responsibilities for camp administration / management. |  |  |  |  | In the context of planned camps/sites as planned emergency response
14 | CCCM | Ensure that the CCCM contingency planning and response strategy adequately mainstream protection principles and standards to guarantee accountability to affected population while focusing on core CCCM activities.
15 | CCCM | Depending on inter-agency discussions on the situation and emerging needs, senior management raise the opportunity to encourage the activation of UNHCR-led CCCM Cluster for conflict-induced displacement scenarios and related cluster coordination arrangements, including possible partnerships (e.g. in camp management).
16 | CCCM | Discuss options for surging staffing capacity in CCCM Cluster Coordination/WG and related IM support to the Cluster, as well as for operational support (e.g. Senior Field Coordinators, Field Officers, CCCM/ Site Management Officers).
17 | CCCM | Within the cluster meeting, discuss and review preparedness levels, mapping of partners’ presence and capacity, contingency planning and response strategy (IASC ERP Approach), and review/ adapt as needed the available tools to support CCCM activities in light of the foreseen emergency scenario.
18 | CCCM | Participate in inter-cluster contingency planning processes (ERP Approach), contribute to the general analysis and provide the Cluster-specific Operational Delivery Plan (IASC ERP Approach).
19 | CCCM | Examine the need/ possibility for establishing operational sub-national coordination fora/ Working Groups or alternative approaches to sub-national coordination and organize training for the designated coordinators.
20 | CCCM | Identify and agree on the necessity to establish new time-bound and subject-focussed technical working groups to develop specific preparedness and response measures (e.g. capacity building) initiatives.
21 | CCCM | Participate actively in the CCCM Cluster as a member and inform the advanced preparedness/ contingency planning discussion, with a view to harmonize UNHCR internal preparedness with the CCCM Cluster contingency planning / response strategy and to adequately support protection mainstreaming. |  |  |  |  | In all situations of conflict or disaster-induced displacement, through field and other relevant staff (notably Shelter and Protection)
|  |  |  | Total | 0 | 0
|  |  |  | Total (report this in first page) | 0